## tasks
ref | subject | description | user_story | sprint | sprint_estimated_start | sprint_estimated_finish | owner | owner_full_name | assigned_to | assigned_to_full_name | status | is_iocaine | is_closed | us_order | taskboard_order | attachments | external_reference | tags | watchers | voters | created_date | modified_date | finished_date
8 | create it |  | 6 | Week 1 | 2018-02-01 | 2018-02-14 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1517510651694 | 0 | 0 |  |  | [] | 0 | 2018-02-01 18:44:11.747160+00:00 | 2018-02-01 18:58:37.704137+00:00 | 2018-02-01 18:53:29.867654+00:00
9 | make the thing |  | 7 | Week 1 | 2018-02-01 | 2018-02-14 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1517510676617 | 0 | 0 |  |  | [] | 0 | 2018-02-01 18:44:36.656821+00:00 | 2018-02-04 19:40:56.469949+00:00 | 2018-02-04 19:40:56.481606+00:00
10 | think of them |  | 5 | Week 1 | 2018-02-01 | 2018-02-14 | NoSquirrels | Benjamin Eversfield | T-Dog | Thomas Makey | Closed | FALSE | TRUE | 1517510712210 | 1 | 0 |  |  | [] | 0 | 2018-02-01 18:45:12.269495+00:00 | 2018-02-07 12:32:24.650182+00:00 | 2018-02-07 12:32:24.657285+00:00
11 | design draft logo |  | 4 | Week 1 | 2018-02-01 | 2018-02-14 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1517510733935 | 1 | 0 |  |  | [] | 0 | 2018-02-01 18:45:33.979869+00:00 | 2018-02-02 21:18:05.386557+00:00 | 2018-02-02 21:05:04.578814+00:00
12 | design draft basket |  | 4 | Week 1 | 2018-02-01 | 2018-02-14 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1517510751146 | 0 | 0 |  |  | [] | 0 | 2018-02-01 18:45:51.190501+00:00 | 2018-02-07 12:32:18.268956+00:00 | 2018-02-07 12:32:18.283018+00:00
13 | invite |  | 6 | Week 1 | 2018-02-01 | 2018-02-14 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1517510768516 | 1 | 0 |  |  | [] | 0 | 2018-02-01 18:46:08.560056+00:00 | 2018-02-03 12:10:05.952260+00:00 | 2018-02-03 12:10:05.966264+00:00
14 | also think of tables |  | 5 | Week 1 | 2018-02-01 | 2018-02-14 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1517510802476 | 0 | 0 |  |  | [] | 0 | 2018-02-01 18:46:42.509667+00:00 | 2018-02-07 12:32:22.909582+00:00 | 2018-02-07 12:32:22.917206+00:00
15 | Test: edit the 'EditMe.php' file |  | 6 | Week 1 | 2018-02-01 | 2018-02-14 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1517511541042 | 2 | 0 |  |  | [] | 0 | 2018-02-01 18:59:01.100788+00:00 | 2018-02-01 18:59:52.242269+00:00 | 2018-02-01 18:59:52.248037+00:00
17 | build db in APEX | write sql script to construct tables (use sequences) | 16 | Sprint 2 | 2018-02-08 | 2018-02-22 | NoSquirrels | Benjamin Eversfield | T-Dog | Thomas Makey | Closed | FALSE | TRUE | 1518114742214 | 2 | 0 |  |  | [] | 0 | 2018-02-08 18:32:22.255456+00:00 | 2018-02-21 18:39:58.145502+00:00 | 2018-02-08 18:54:04.019324+00:00
18 | add test data | add test data for customer, seller, product listing, and reviews | 16 | Sprint 2 | 2018-02-08 | 2018-02-22 | NoSquirrels | Benjamin Eversfield | T-Dog | Thomas Makey | Closed | FALSE | TRUE | 1518114876757 | 3 | 0 |  |  | [] | 0 | 2018-02-08 18:34:36.792885+00:00 | 2018-02-21 18:40:01.616679+00:00 | 2018-02-08 18:54:07.478156+00:00
19 | Update ERD | update ERD to reflect current database, upload to C9 | 16 | Sprint 2 | 2018-02-08 | 2018-02-22 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1518115014799 | 4 | 0 |  |  | [] | 0 | 2018-02-08 18:36:54.875963+00:00 | 2018-02-21 18:40:05.866704+00:00 | 2018-02-08 18:54:05.807721+00:00
21 | Test colour scheme on basic non-functional html template | using #F1EACE as main in adobe analogous, develop and test out colour scheme | 20 | Sprint 2 | 2018-02-08 | 2018-02-22 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1518116181394 | 1 | 0 |  |  | [] | 0 | 2018-02-08 18:56:21.449407+00:00 | 2018-02-21 18:39:44.571866+00:00 | 2018-02-11 15:50:56.839500+00:00
22 | apply colour scheme for group review | Once test front page has been assembled, edit css to incorporate colour scheme | 20 | Sprint 2 | 2018-02-08 | 2018-02-22 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1518116336707 | 2 | 0 |  |  | [] | 0 | 2018-02-08 18:58:56.745219+00:00 | 2018-02-21 18:39:49.509415+00:00 | 2018-02-14 11:16:19.501937+00:00
23 | build trigger for quantity column | Exactly what is says on the tin | 16 | Sprint 2 | 2018-02-08 | 2018-02-22 | NoSquirrels | Benjamin Eversfield | T-Dog | Thomas Makey | Closed | FALSE | TRUE | 1518116393028 | 1 | 0 |  |  | [] | 0 | 2018-02-08 18:59:53.079027+00:00 | 2018-02-24 12:39:49.917928+00:00 | 2018-02-24 12:39:49.923664+00:00
25 | Complete and upload charter | Complete and upload charter | 24 | Sprint 2 | 2018-02-08 | 2018-02-22 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1518116505469 | 1 | 0 |  |  | [] | 0 | 2018-02-08 19:01:45.511928+00:00 | 2018-02-21 18:39:13.825390+00:00 | 2018-02-11 12:00:30.036312+00:00
27 | Create list of all pages needed and their function within the site | as above | 26 | Sprint 2 | 2018-02-08 | 2018-02-22 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1518117075652 | 4 | 0 |  |  | [] | 0 | 2018-02-08 19:11:15.702189+00:00 | 2018-02-21 18:39:34.294529+00:00 | 2018-02-12 10:31:34.956530+00:00
28 | Begin coding of page funcitonality | Create code for login (example) as functionality not dependant on style | 26 | Sprint 2 | 2018-02-08 | 2018-02-22 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1518117149567 | 3 | 0 |  |  | [] | 0 | 2018-02-08 19:12:29.606228+00:00 | 2018-02-21 18:39:32.074720+00:00 | 2018-02-17 11:31:01.101189+00:00
30 | create list of user stories | Create list of user stories and upload to C9 | 29 | Sprint 2 | 2018-02-08 | 2018-02-22 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1518117360058 | 1 | 0 |  |  | [] | 0 | 2018-02-08 19:16:00.125182+00:00 | 2018-02-21 18:39:15.257575+00:00 | 2018-02-14 11:16:04.705695+00:00
32 | Create customer profiles | Create inserts for customer table | 31 | Sprint 2 | 2018-02-08 | 2018-02-22 | NoSquirrels | Benjamin Eversfield | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1518117864099 | 1 | 0 |  |  | [] | 0 | 2018-02-08 19:24:24.169168+00:00 | 2018-02-21 18:39:20.067039+00:00 | 2018-02-16 14:16:56.725493+00:00
33 | create Seller profiles | Create data inserts for seller table | 31 | Sprint 2 | 2018-02-08 | 2018-02-22 | NoSquirrels | Benjamin Eversfield | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1518117942854 | 2 | 0 |  |  | [] | 0 | 2018-02-08 19:25:42.892537+00:00 | 2018-02-21 18:39:25.022362+00:00 | 2018-02-16 14:16:58.352898+00:00
35 | Construct working full page html | build front page to include all sections (using PHP includes) with responsive design utilising the foundation framework | 34 | Sprint 2 | 2018-02-08 | 2018-02-22 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1518118424403 | 1 | 0 |  |  | [] | 0 | 2018-02-08 19:33:44.494589+00:00 | 2018-02-24 12:39:40.109238+00:00 | 2018-02-24 12:39:40.114961+00:00
36 | Create latest product and top seller cards | include the cards in the design and, if possible, generate them dynamically with PHP. | 34 | Sprint 2 | 2018-02-08 | 2018-02-22 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1518118553092 | 3 | 0 |  |  | [] | 0 | 2018-02-08 19:35:53.133411+00:00 | 2018-02-21 18:39:42.179566+00:00 | 2018-02-20 16:41:30.720079+00:00
38 | create new colour scheme based on feedback |  | 20 | Sprint 2 | 2018-02-08 | 2018-02-22 | humanmale | Dylan Ellis | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1518607007347 | 3 | 0 |  |  | [] | 0 | 2018-02-14 11:16:47.381290+00:00 | 2018-02-21 18:39:45.572788+00:00 | 2018-02-20 23:28:35.776989+00:00
39 | Create seller registration page | Create a basic registration page for sellers. This page needs to collect details then add a new account to the database. | 26 | Sprint 2 | 2018-02-08 | 2018-02-22 | humanmale | Dylan Ellis | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1518607521306 | 1 | 0 |  |  | [] | 0 | 2018-02-14 11:25:21.360043+00:00 | 2018-02-22 12:19:59.490388+00:00 | 2018-02-21 22:11:32.539794+00:00
40 | Create page banner |  | 34 | Sprint 2 | 2018-02-08 | 2018-02-22 | humanmale | Dylan Ellis | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1518607709474 | 2 | 0 |  |  | [] | 0 | 2018-02-14 11:28:29.515357+00:00 | 2018-02-21 18:39:37.275730+00:00 | 2018-02-14 11:28:29.553832+00:00
41 | Create customer registration page | Create a page for customers to create an account. | 26 | Sprint 2 | 2018-02-08 | 2018-02-22 | humanmale | Dylan Ellis | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1518608192547 | 2 | 0 |  |  | [] | 0 | 2018-02-14 11:36:32.585404+00:00 | 2018-02-21 18:39:30.078378+00:00 | 2018-02-21 18:39:30.093099+00:00
52 | Create Reviews | Create 3 reviews for each seller |  | Sprint 2 | 2018-02-08 | 2018-02-22 | HabibKhan | Habib Khan | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1518790673363 | 0 | 0 |  |  | [] | 0 | 2018-02-16 14:17:53.427544+00:00 | 2018-02-24 12:40:00.446303+00:00 | 2018-02-24 12:40:00.456206+00:00
53 | Amend Onions Table Data | Add addresses for sellers |  | Sprint 2 | 2018-02-08 | 2018-02-22 | HabibKhan | Habib Khan | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1518790750343 | 1518790750344 | 0 |  |  | [] | 0 | 2018-02-16 14:19:10.379170+00:00 | 2018-02-24 12:40:10.986538+00:00 | 2018-02-24 12:40:10.993857+00:00
89 | Decide on colour scheme, validated by team |  | 91 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1519477062041 | 4 | 0 |  |  | [] | 0 | 2018-02-24 12:57:42.079940+00:00 | 2018-03-01 13:04:32.441837+00:00 | 2018-02-26 19:53:05.994686+00:00
90 | Apply validated colour scheme to site |  | 88 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1519477087386 | 0 | 0 |  |  | [] | 0 | 2018-02-24 12:58:07.421871+00:00 | 2018-03-01 13:04:49.502653+00:00 | 2018-03-01 13:04:49.510874+00:00
92 | Create code to run default "select all" query for products page and test, no css just outputs to white page |  | 91 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1519477334720 | 2 | 0 |  |  | [] | 0 | 2018-02-24 13:02:14.760509+00:00 | 2018-03-01 13:04:29.725098+00:00 | 2018-02-27 21:44:46.591839+00:00
93 | add drop down menu for onion type (and any other variables and appropriate interface (check box etc)) |  | 91 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1519477382630 | 1 | 0 |  |  | [] | 0 | 2018-02-24 13:03:02.669591+00:00 | 2018-03-01 13:04:30.785680+00:00 | 2018-02-27 21:44:51.343599+00:00
94 | add open text box search (ie customer remembers only part of description, searches for "dorset" etc) |  | 91 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1519477443109 | 3 | 0 |  |  | [] | 0 | 2018-02-24 13:04:03.147902+00:00 | 2018-03-01 13:04:26.672246+00:00 | 2018-02-27 21:44:56.493104+00:00
95 | integrate tested code into products page and test |  | 91 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1519477505370 | 0 | 0 |  |  | [] | 0 | 2018-02-24 13:05:05.414165+00:00 | 2018-03-01 13:04:27.766181+00:00 | 2018-02-27 21:44:58.781180+00:00
97 | setup folder on cloud9 for user uploaded images |  | 96 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1519477732191 | 0 | 0 |  |  | [] | 0 | 2018-02-24 13:08:52.226180+00:00 | 2018-03-01 13:04:25.033279+00:00 | 2018-02-26 12:59:48.063976+00:00
98 | add image upload to seller registration (and customer?) |  | 96 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1519477890075 | 1 | 0 |  |  | [] | 0 | 2018-02-24 13:11:30.110668+00:00 | 2018-03-01 13:11:53.388933+00:00 | 2018-03-01 13:11:53.401463+00:00
100 | Create html/css template for seller info page (as viewed by customer) |  | 99 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | T-Dog | Thomas Makey | Closed | FALSE | TRUE | 1519478144846 | 0 | 0 |  |  | [] | 0 | 2018-02-24 13:15:44.884575+00:00 | 2018-03-01 13:03:49.528288+00:00 | 2018-02-27 13:44:43.872787+00:00
101 | incorporate php to diplay seller name, member since(?), average review score, number of reviews, seller information and three (or four) reviews |  | 99 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | T-Dog | Thomas Makey | Closed | FALSE | TRUE | 1519478249688 | 2 | 0 |  |  | [] | 0 | 2018-02-24 13:17:29.719195+00:00 | 2018-03-01 13:03:51.133355+00:00 | 2018-02-27 17:10:12.523540+00:00
102 | photo will be pulled from db, needs default behaviour if no image set |  | 99 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | T-Dog | Thomas Makey | Closed | FALSE | TRUE | 1519478296470 | 1 | 0 |  |  | [] | 0 | 2018-02-24 13:18:16.504422+00:00 | 2018-03-01 13:03:52.159457+00:00 | 2018-02-27 17:10:07.565902+00:00
104 | Complete reviews entries and assign to sellers |  | 103 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1519478395989 | 0 | 0 |  |  | [] | 0 | 2018-02-24 13:19:56.019175+00:00 | 2018-03-01 13:04:21.306592+00:00 | 2018-02-24 16:01:53.888820+00:00
105 | enter data for extended customer address fields |  | 103 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1519478425503 | 1 | 0 |  |  | [] | 0 | 2018-02-24 13:20:25.549867+00:00 | 2018-03-01 13:04:22.288976+00:00 | 2018-02-24 16:01:58.041816+00:00
106 | find images of onions (alter if necessary to 250x250), store in subfolder in images folder on cloud9 |  | 103 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1519478596196 | 3 | 0 |  |  | [] | 0 | 2018-02-24 13:23:16.233694+00:00 | 2018-03-01 13:11:48.140185+00:00 | 2018-03-01 13:11:48.160531+00:00
108 | Create html/template for products listing pafge to be viewed by user, will have section reserved for search at the top |  | 107 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1519479022169 | 1 | 0 |  |  | [] | 0 | 2018-02-24 13:30:22.200647+00:00 | 2018-03-01 13:03:54.923674+00:00 | 2018-02-26 15:12:04.204036+00:00
109 | write stand-in php to select all products from database |  | 107 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1519479099843 | 0 | 0 |  |  | [] | 0 | 2018-02-24 13:31:39.871716+00:00 | 2018-03-01 13:03:53.202255+00:00 | 2018-02-26 13:10:11.518252+00:00
110 | use of foundation to display product cards, name and seller information that link appropriately |  | 107 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1519479155967 | 2 | 0 |  |  | [] | 0 | 2018-02-24 13:32:36.016680+00:00 | 2018-03-01 13:03:54.076753+00:00 | 2018-02-26 15:11:57.984115+00:00
112 | create html/css template for individual item page (w/ item photo, product name, seller name, price per unit, delivery info, quantity selector, big "add to basket" button |  | 111 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1519479581210 | 0 | 0 |  |  | [] | 0 | 2018-02-24 13:39:41.242002+00:00 | 2018-03-01 13:11:43.270107+00:00 | 2018-03-01 13:11:43.278214+00:00
113 | php to pull relevent data from the base of data |  | 111 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1519479708496 | 2 | 0 |  |  | [] | 0 | 2018-02-24 13:41:48.547262+00:00 | 2018-03-01 13:11:44.590727+00:00 | 2018-03-01 13:11:44.598937+00:00
114 | quantity select list mustn't offer more delicious onions than there are currently stuffed in the databasotron |  | 111 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1519479778266 | 1 | 0 |  |  | [] | 0 | 2018-02-24 13:42:58.322785+00:00 | 2018-03-01 13:11:45.752014+00:00 | 2018-03-01 13:11:45.776931+00:00
116 | create trigger to reduce "available stock" data on submission of order |  | 115 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1519479949373 | 1 | 0 |  |  | [] | 0 | 2018-02-24 13:45:49.405640+00:00 | 2018-03-01 13:04:02.343860+00:00 | 2018-02-26 18:50:33.354535+00:00
117 | Check products table fields are correct, populate table with test data |  | 115 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1519479990799 | 3 | 0 |  |  | [] | 0 | 2018-02-24 13:46:30.855854+00:00 | 2018-03-01 13:04:00.192926+00:00 | 2018-02-25 14:59:06.248744+00:00
118 | Create orders and order items to test data base functions correctly, i'm not looking forward to this bit |  | 115 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1519480055880 | 4 | 0 |  |  | [] | 0 | 2018-02-24 13:47:35.914432+00:00 | 2018-03-01 13:03:58.350938+00:00 | 2018-02-26 18:50:42.635939+00:00
119 | alter seller and customer logins to be unique |  | 115 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1519480670162 | 0 | 0 |  |  | [] | 0 | 2018-02-24 13:57:50.199540+00:00 | 2018-03-01 13:03:57.285957+00:00 | 2018-02-27 17:19:41.294357+00:00
120 | create an admin account and remove admin privileges from sellers |  | 115 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1519480697592 | 2 | 0 |  |  | [] | 0 | 2018-02-24 13:58:17.635081+00:00 | 2018-03-01 13:04:00.890709+00:00 | 2018-02-24 18:42:13.577632+00:00
122 | create basic template that shows items and quanties, totals in table, customer delivery details, has purchase button. |  | 121 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1519480927940 | 1 | 0 |  |  | [] | 0 | 2018-02-24 14:02:08.021754+00:00 | 2018-03-01 13:04:19.114642+00:00 | 2018-02-27 14:46:10.333646+00:00
123 | Create stand in code to populate order table from stand-in session variables, pull data from db with php |  | 121 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1519481051688 | 0 | 0 |  |  | [] | 0 | 2018-02-24 14:04:11.728277+00:00 | 2018-03-01 13:04:17.046514+00:00 | 2018-02-26 18:51:03.776527+00:00
124 | click of purchase button updates order and order item tables, fires trigger and clears item session data |  | 121 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1519481091500 | 2 | 0 |  |  | [] | 0 | 2018-02-24 14:04:51.540236+00:00 | 2018-03-01 13:04:18.161458+00:00 | 2018-02-27 14:31:25.276053+00:00
125 | Populate Products table (please) |  | 103 | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1519570814039 | 2 | 0 |  |  | [] | 0 | 2018-02-25 15:00:14.075995+00:00 | 2018-03-01 13:11:49.450990+00:00 | 2018-03-01 13:11:49.459225+00:00
127 | Do the populating of the productings tablers |  | 126 | Sprint 4 aka Ronald | 2018-03-01 | 2018-03-07 | NoSquirrels | Benjamin Eversfield | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1519924500832 | 0 | 0 |  |  | [] | 0 | 2018-03-01 17:15:00.882903+00:00 | 2018-03-06 12:10:23.492785+00:00 | 2018-03-06 12:10:23.500489+00:00
129 | Get them. Yes, get them. |  | 128 | Sprint 4 aka Ronald | 2018-03-01 | 2018-03-07 | NoSquirrels | Benjamin Eversfield | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1519924562144 | 0 | 0 |  |  | [] | 0 | 2018-03-01 17:16:02.189070+00:00 | 2018-03-06 12:10:29.684469+00:00 | 2018-03-06 12:10:29.691349+00:00
130 | Upload the images to c9 with correct filenames |  | 128 | Sprint 4 aka Ronald | 2018-03-01 | 2018-03-07 | NoSquirrels | Benjamin Eversfield | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1519924585678 | 1 | 0 |  |  | [] | 0 | 2018-03-01 17:16:25.715781+00:00 | 2018-03-03 11:47:29.573636+00:00 | 2018-03-03 11:47:29.582287+00:00
132 | Ensure that registration forms behave as intended |  | 131 | Sprint 4 aka Ronald | 2018-03-01 | 2018-03-07 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1519924701903 | 0 | 0 |  |  | [] | 0 | 2018-03-01 17:18:21.943439+00:00 | 2018-03-21 14:30:45.192643+00:00 | 2018-03-21 14:30:45.207312+00:00
133 | Ensure that registration forms look the same and are lovely to behold |  | 131 | Sprint 4 aka Ronald | 2018-03-01 | 2018-03-07 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1519924723869 | 1 | 0 |  |  | [] | 0 | 2018-03-01 17:18:43.937173+00:00 | 2018-03-06 00:51:33.326821+00:00 | 2018-03-06 00:51:33.332282+00:00
135 | Make login form look better |  | 134 | Sprint 4 aka Ronald | 2018-03-01 | 2018-03-07 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1519924793719 | 1 | 0 |  |  | [] | 0 | 2018-03-01 17:19:53.763346+00:00 | 2018-03-05 13:29:04.048147+00:00 | 2018-03-05 13:29:04.060065+00:00
136 | address login form user session variable bug (set to user id, not user in. booleans for user/seller/admin?) |  | 134 | Sprint 4 aka Ronald | 2018-03-01 | 2018-03-07 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1519924906401 | 0 | 0 |  |  | [] | 0 | 2018-03-01 17:21:46.441798+00:00 | 2018-03-05 13:14:48.082093+00:00 | 2018-03-05 13:14:48.096258+00:00
137 | Sort out nav bar issue where admin panel appears regardless of user |  | 134 | Sprint 4 aka Ronald | 2018-03-01 | 2018-03-07 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1519924927627 | 3 | 0 |  |  | [] | 0 | 2018-03-01 17:22:07.667231+00:00 | 2018-03-05 13:14:52.019187+00:00 | 2018-03-05 13:14:52.030904+00:00
138 | sort out nav bar issue where looks for userIn isset (which can happen in failed login) |  | 134 | Sprint 4 aka Ronald | 2018-03-01 | 2018-03-07 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1519924951621 | 5 | 0 |  |  | [] | 0 | 2018-03-01 17:22:31.657013+00:00 | 2018-03-05 13:17:03.840472+00:00 | 2018-03-05 13:17:03.850797+00:00
139 | Complete basket |  | 134 | Sprint 4 aka Ronald | 2018-03-01 | 2018-03-07 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1519924961211 | 2 | 0 |  |  | [] | 0 | 2018-03-01 17:22:41.261318+00:00 | 2018-03-05 13:19:28.896165+00:00 | 2018-03-05 13:19:28.923960+00:00
140 | mend footer css |  | 134 | Sprint 4 aka Ronald | 2018-03-01 | 2018-03-07 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1519924969629 | 4 | 0 |  |  | [] | 0 | 2018-03-01 17:22:49.658146+00:00 | 2018-03-05 13:17:05.835982+00:00 | 2018-03-05 13:17:05.842699+00:00
142 | complete and tidy up seller and customer and item related pages. You know what to do. |  | 141 | Sprint 4 aka Ronald | 2018-03-01 | 2018-03-07 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1519925045165 | 0 | 0 |  |  | [] | 0 | 2018-03-01 17:24:05.199610+00:00 | 2018-03-21 14:30:44.371124+00:00 | 2018-03-21 14:30:44.378983+00:00
144 | Create a welcome page for customer once login. have welcome message, current details that sort of stuff. link to amend page. |  | 143 | Sprint 4 aka Ronald | 2018-03-01 | 2018-03-07 | NoSquirrels | Benjamin Eversfield | T-Dog | Thomas Makey | Closed | FALSE | TRUE | 1519925194297 | 0 | 0 |  |  | [] | 0 | 2018-03-01 17:26:34.336053+00:00 | 2018-03-06 13:26:29.088484+00:00 | 2018-03-06 13:26:29.097718+00:00
145 | amend details page. pulls and populates form from dB, resubmits and overwrites. |  | 143 | Sprint 4 aka Ronald | 2018-03-01 | 2018-03-07 | NoSquirrels | Benjamin Eversfield | T-Dog | Thomas Makey | Closed | FALSE | TRUE | 1519925227856 | 1 | 0 |  |  | [] | 0 | 2018-03-01 17:27:07.924861+00:00 | 2018-03-21 14:30:43.398872+00:00 | 2018-03-21 14:30:43.417869+00:00
147 | Create page for basket to redirect to containing completion message |  | 146 | Sprint 5 aka Melanie | 2018-03-21 | 2018-03-27 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1521643315739 | 0 | 0 |  |  | [] | 0 | 2018-03-21 14:41:55.768412+00:00 | 2018-03-24 18:26:49.284624+00:00 | 2018-03-24 18:26:25.510664+00:00
150 | Generate unique order number and store in database |  | 146 | Sprint 5 aka Melanie | 2018-03-21 | 2018-03-27 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1521644061531 | 1 | 0 |  |  | [] | 0 | 2018-03-21 14:54:21.574142+00:00 | 2018-03-24 18:26:52.101573+00:00 | 2018-03-24 18:26:28.068840+00:00
152 | acquire images |  | 151 | Sprint 5 aka Melanie | 2018-03-21 | 2018-03-27 | NoSquirrels | Benjamin Eversfield | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1521652435261 | 0 | 0 |  |  | [] | 0 | 2018-03-21 17:13:55.296224+00:00 | 2018-03-29 17:12:30.350112+00:00 | 2018-03-29 16:58:31.661823+00:00
153 | resize and compress images |  | 151 | Sprint 5 aka Melanie | 2018-03-21 | 2018-03-27 | NoSquirrels | Benjamin Eversfield | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1521652447882 | 1 | 0 |  |  | [] | 0 | 2018-03-21 17:14:07.918827+00:00 | 2018-03-29 17:12:33.709878+00:00 | 2018-03-29 16:58:32.435137+00:00
154 | upload to c9 in relevant folder |  | 151 | Sprint 5 aka Melanie | 2018-03-21 | 2018-03-27 | NoSquirrels | Benjamin Eversfield | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1521652463256 | 2 | 0 |  |  | [] | 0 | 2018-03-21 17:14:23.321724+00:00 | 2018-03-29 17:12:31.420774+00:00 | 2018-03-29 16:58:34.991920+00:00
156 | Create well-laid-out page that is visually appealing, functional and self explanatory |  | 155 | Sprint 5 aka Melanie | 2018-03-21 | 2018-03-27 | NoSquirrels | Benjamin Eversfield | T-Dog | Thomas Makey | Closed | FALSE | TRUE | 1521652820879 | 2 | 0 |  |  | [] | 0 | 2018-03-21 17:20:20.908879+00:00 | 2018-03-29 17:22:00.047040+00:00 | 2018-03-29 17:22:00.053528+00:00
157 | Create look-ups to pull relevant data from database to display to seller |  | 155 | Sprint 5 aka Melanie | 2018-03-21 | 2018-03-27 | NoSquirrels | Benjamin Eversfield | T-Dog | Thomas Makey | Closed | FALSE | TRUE | 1521652844934 | 0 | 0 |  |  | [] | 0 | 2018-03-21 17:20:44.968145+00:00 | 2018-03-29 17:22:02.910398+00:00 | 2018-03-29 17:22:02.915747+00:00
158 | Add functionality to amend seller details |  | 155 | Sprint 5 aka Melanie | 2018-03-21 | 2018-03-27 | NoSquirrels | Benjamin Eversfield | T-Dog | Thomas Makey | Closed | FALSE | TRUE | 1521653109743 | 1 | 0 |  |  | [] | 0 | 2018-03-21 17:25:09.776207+00:00 | 2018-03-29 17:22:07.108482+00:00 | 2018-03-29 17:22:07.114093+00:00
160 | alter logo and basket icon padding/margins to create evenness, well-being and a consistent nav bar height. |  | 159 | Sprint 5 aka Melanie | 2018-03-21 | 2018-03-27 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1521653608251 | 1 | 0 |  |  | [] | 0 | 2018-03-21 17:33:28.295530+00:00 | 2018-03-29 17:18:17.746349+00:00 | 2018-03-29 17:18:17.754397+00:00
161 | Restyle seller information page to be more open and neat, remove deprecated html such as <u> tags to maintain separation of data from style. Reference wireframes and websites |  | 159 | Sprint 5 aka Melanie | 2018-03-21 | 2018-03-27 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1521653705523 | 3 | 0 |  |  | [] | 0 | 2018-03-21 17:35:05.562463+00:00 | 2018-03-29 17:18:20.494424+00:00 | 2018-03-29 17:18:20.499655+00:00
162 | Make logo a link to home page as per convention |  | 159 | Sprint 5 aka Melanie | 2018-03-21 | 2018-03-27 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1521653750049 | 0 | 0 |  |  | [] | 0 | 2018-03-21 17:35:50.087808+00:00 | 2018-03-29 17:18:14.796974+00:00 | 2018-03-28 22:56:16.187839+00:00
163 | Investigate image loading issue on home page |  | 159 | Sprint 5 aka Melanie | 2018-03-21 | 2018-03-27 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1521653767517 | 2 | 0 |  |  | [] | 0 | 2018-03-21 17:36:07.553680+00:00 | 2018-03-29 17:18:22.705699+00:00 | 2018-03-29 17:18:22.711724+00:00
165 | Create admin home page, ensure admin is redirected there from login. Page has clear buttons/links to pages offering specific admin functionality |  | 164 | Sprint 5 aka Melanie | 2018-03-21 | 2018-03-27 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1521654555685 | 2 | 0 |  |  | [] | 0 | 2018-03-21 17:49:15.722177+00:00 | 2018-03-29 16:37:45.986297+00:00 | 2018-03-29 10:05:48.679074+00:00
166 | Create page to view all sellers, customers and (for now) delete an entry |  | 164 | Sprint 5 aka Melanie | 2018-03-21 | 2018-03-27 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1521654594726 | 1 | 0 |  |  | [] | 0 | 2018-03-21 17:49:54.774545+00:00 | 2018-03-29 16:37:47.648066+00:00 | 2018-03-29 10:06:04.420068+00:00
167 | Create page to view all orders, each order name? number? is a link to its list of items. Can delete order. |  | 164 | Sprint 5 aka Melanie | 2018-03-21 | 2018-03-27 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1521654656003 | 0 | 0 |  |  | [] | 0 | 2018-03-21 17:50:56.073625+00:00 | 2018-03-29 16:37:48.822150+00:00 | 2018-03-29 10:05:54.309817+00:00
169 | upload images to correct c9 folder |  | 168 | Sprint 6 aka Deborah | 2018-03-29 | 2018-04-04 | NoSquirrels | Benjamin Eversfield | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1522345199455 | 0 | 0 |  |  | [] | 0 | 2018-03-29 17:39:59.485652+00:00 | 2018-04-04 14:04:05.610880+00:00 | 2018-04-04 11:47:28.152664+00:00
170 | amend database so that image names in db are correct to those in c9 |  | 168 | Sprint 6 aka Deborah | 2018-03-29 | 2018-04-04 | NoSquirrels | Benjamin Eversfield | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1522345250764 | 2 | 0 |  |  | [] | 0 | 2018-03-29 17:40:50.799219+00:00 | 2018-04-05 16:52:30.268364+00:00 | 2018-04-05 09:55:59.629101+00:00
171 | pass completed and error-check sql to database manager |  | 168 | Sprint 6 aka Deborah | 2018-03-29 | 2018-04-04 | NoSquirrels | Benjamin Eversfield | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1522345280794 | 1 | 0 |  |  | [] | 0 | 2018-03-29 17:41:20.827197+00:00 | 2018-04-05 16:52:33.203618+00:00 | 2018-04-05 16:52:33.211667+00:00
173 | alter logo and basket icon padding/margins to create evenness, well-being and a consistent nav bar height. |  | 172 | Sprint 6 aka Deborah | 2018-03-29 | 2018-04-04 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1522347358168 | 0 | 0 |  |  | [] | 0 | 2018-03-29 18:15:58.208367+00:00 | 2018-04-04 13:58:26.361033+00:00 | 2018-04-01 18:21:34.634226+00:00
174 | Restyle seller information page to be more open and neat, remove deprecated html such as <u> tags to maintain separation of data from style. Reference wireframes and websites |  | 172 | Sprint 6 aka Deborah | 2018-03-29 | 2018-04-04 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1522347386161 | 1 | 0 |  |  | [] | 0 | 2018-03-29 18:16:26.193277+00:00 | 2018-04-05 17:09:10.186428+00:00 | 2018-04-05 11:07:58.650046+00:00
176 | change review table output to individual boxes with quote and name (name in italics) |  | 175 | Sprint 6 aka Deborah | 2018-03-29 | 2018-04-04 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1522347539265 | 0 | 0 |  |  | [] | 0 | 2018-03-29 18:18:59.296597+00:00 | 2018-03-30 13:53:36.930298+00:00 | 2018-03-30 13:53:36.935710+00:00
178 | Build page using correct syntax to select, delete, update |  | 177 | Sprint 6 aka Deborah | 2018-03-29 | 2018-04-04 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1522347702556 | 1 | 0 |  |  | [] | 0 | 2018-03-29 18:21:42.589839+00:00 | 2018-04-04 14:32:14.347911+00:00 | 2018-04-04 14:32:14.355159+00:00
179 | research php needed for connection and queries on Apex db |  | 177 | Sprint 6 aka Deborah | 2018-03-29 | 2018-04-04 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1522347721898 | 0 | 0 |  |  | [] | 0 | 2018-03-29 18:22:01.935968+00:00 | 2018-04-04 14:32:12.032642+00:00 | 2018-04-04 14:32:12.038907+00:00
181 | Create well-laid-out page that is visually appealing, functional and self explanatory |  | 180 | Sprint 6 aka Deborah | 2018-03-29 | 2018-04-04 | NoSquirrels | Benjamin Eversfield | T-Dog | Thomas Makey | Closed | FALSE | TRUE | 1522348015395 | 2 | 0 |  |  | [] | 0 | 2018-03-29 18:26:55.448663+00:00 | 2018-04-05 16:51:44.307882+00:00 | 2018-04-05 14:53:08.138604+00:00
182 | Create look-ups to pull relevant data from database to display to seller |  | 180 | Sprint 6 aka Deborah | 2018-03-29 | 2018-04-04 | NoSquirrels | Benjamin Eversfield | T-Dog | Thomas Makey | Closed | FALSE | TRUE | 1522348035158 | 1 | 0 |  |  | [] | 0 | 2018-03-29 18:27:15.197023+00:00 | 2018-04-05 16:51:45.451732+00:00 | 2018-04-05 14:53:07.039358+00:00
183 | Add functionality to amend seller details |  | 180 | Sprint 6 aka Deborah | 2018-03-29 | 2018-04-04 | NoSquirrels | Benjamin Eversfield | T-Dog | Thomas Makey | Closed | FALSE | TRUE | 1522348047827 | 0 | 0 |  |  | [] | 0 | 2018-03-29 18:27:27.853876+00:00 | 2018-04-05 16:51:43.406836+00:00 | 2018-04-05 14:52:58.816242+00:00
185 | Have amend/update seller/customer option in crud table, link redirects to update page |  | 184 | Sprint 6 aka Deborah | 2018-03-29 | 2018-04-04 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1522348247345 | 0 | 0 |  |  | [] | 0 | 2018-03-29 18:30:47.372974+00:00 | 2018-04-04 14:00:44.814373+00:00 | 2018-04-02 11:25:58.328235+00:00
186 | update page displays all data, allows update of all data except seller_id |  | 184 | Sprint 6 aka Deborah | 2018-03-29 | 2018-04-04 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1522348271004 | 1 | 0 |  |  | [] | 0 | 2018-03-29 18:31:11.035372+00:00 | 2018-04-04 14:00:41.611445+00:00 | 2018-04-02 11:25:54.690194+00:00
187 | add to query for sellers page to not pull seller_id 31 as this is the admin row |  | 172 | Sprint 6 aka Deborah | 2018-03-29 | 2018-04-04 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1522401719801 | 2 | 0 |  |  | [] | 0 | 2018-03-30 09:21:59.860036+00:00 | 2018-04-05 11:39:56.449656+00:00 | 2018-04-05 11:39:56.456677+00:00
189 | Research what personas are in the context of an e-commerce website to gain full understanding |  | 188 | Sprint 7 aka Wilhelm | 2018-04-05 | 2018-04-12 | NoSquirrels | Benjamin Eversfield | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1522950578035 | 0 | 0 |  |  | [] | 0 | 2018-04-05 17:49:38.066208+00:00 | 2018-04-12 08:58:13.800482+00:00 | 2018-04-12 08:57:36.756156+00:00
190 | Decide the brand specific personas that io.io is marketing to |  | 201 | Sprint 7 aka Wilhelm | 2018-04-05 | 2018-04-12 | NoSquirrels | Benjamin Eversfield | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1522950607957 | 3 | 0 |  |  | [] | 0 | 2018-04-05 17:50:07.989211+00:00 | 2018-04-12 08:58:12.904954+00:00 | 2018-04-12 08:57:37.856292+00:00
191 | Produce a document to be presented to assessors listing the personas and a description of how io.io attracts and satisfies them |  | 201 | Sprint 7 aka Wilhelm | 2018-04-05 | 2018-04-12 | NoSquirrels | Benjamin Eversfield | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1522950647529 | 2 | 0 |  |  | [] | 0 | 2018-04-05 17:50:47.560768+00:00 | 2018-04-12 08:58:11.169170+00:00 | 2018-04-12 08:57:35.505754+00:00
193 | Fix the links so that the amendment form loads in the homepage frame |  | 192 | Sprint 7 aka Wilhelm | 2018-04-05 | 2018-04-12 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1522951008158 | 0 | 0 |  |  | [] | 0 | 2018-04-05 17:56:48.188142+00:00 | 2018-04-08 11:31:56.856503+00:00 | 2018-04-08 11:31:56.863906+00:00
195 | Alter "add to basket" button code so that if no one is logged in it redirects to login, display the correct text in the button. If seller or admin logs in, add to basket button is displayed but is greyed out and unusable. |  | 194 | Sprint 7 aka Wilhelm | 2018-04-05 | 2018-04-12 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1522951137726 | 0 | 0 |  |  | [] | 0 | 2018-04-05 17:58:57.759614+00:00 | 2018-04-08 13:14:35.961384+00:00 | 2018-04-08 13:14:35.967781+00:00
197 | Produce updated ERD that has correct tables, rows and data types and limits. |  | 196 | Sprint 7 aka Wilhelm | 2018-04-05 | 2018-04-12 | NoSquirrels | Benjamin Eversfield | T-Dog | Thomas Makey | Closed | FALSE | TRUE | 1522951502120 | 0 | 0 |  |  | [] | 0 | 2018-04-05 18:05:02.157852+00:00 | 2018-04-12 17:48:00.737291+00:00 | 2018-04-12 17:48:00.743767+00:00
199 | Add customer first name, seller's company name or "admin" to the navbar welcome to be displayed when the relevant user-type logs in. |  | 198 | Sprint 7 aka Wilhelm | 2018-04-05 | 2018-04-12 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1522951716695 | 1 | 0 |  |  | [] | 0 | 2018-04-05 18:08:36.729904+00:00 | 2018-04-11 07:32:42.373977+00:00 | 2018-04-10 21:13:55.903750+00:00
200 | Add "my page" link to navbar for seller accounts, linking to relevant seller's home page. |  | 198 | Sprint 7 aka Wilhelm | 2018-04-05 | 2018-04-12 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1522951857936 | 0 | 0 |  |  | [] | 0 | 2018-04-05 18:10:57.965897+00:00 | 2018-04-11 07:32:39.678153+00:00 | 2018-04-11 07:32:27.161694+00:00
202 | Think of useful way reports could be generated (admin: traffic? Seller: sales?) |  | 201 | Sprint 7 aka Wilhelm | 2018-04-05 | 2018-04-12 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1522952201033 | 0 | 0 |  |  | [] | 0 | 2018-04-05 18:16:41.063449+00:00 | 2018-04-11 14:55:14.922383+00:00 | 2018-04-11 14:55:14.934910+00:00
203 | Research embedding report in webpage. |  | 201 | Sprint 7 aka Wilhelm | 2018-04-05 | 2018-04-12 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1522952221206 | 1 | 0 |  |  | [] | 0 | 2018-04-05 18:17:01.238474+00:00 | 2018-04-11 14:55:18.774826+00:00 | 2018-04-11 14:55:18.785484+00:00
205 | Remove duplicate ID's in equalizer divs and replace with classes |  | 204 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1523555481576 | 4 | 0 |  |  | [] | 0 | 2018-04-12 17:51:21.610833+00:00 | 2018-04-14 12:50:42.479079+00:00 | 2018-04-14 12:50:42.486867+00:00
207 | solve centring issues on headers |  | 206 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1523555741747 | 0 | 0 |  |  | [] | 0 | 2018-04-12 17:55:41.789235+00:00 | 2018-04-17 08:44:56.698421+00:00 | 2018-04-17 08:44:56.709309+00:00
208 | Neaten the individual product page layout |  | 206 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1523555769691 | 3 | 0 |  |  | [] | 0 | 2018-04-12 17:56:09.731827+00:00 | 2018-04-14 18:40:45.990899+00:00 | 2018-04-14 18:33:33.642043+00:00
209 | Take decisive action to resolve the button design issue |  | 206 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1523555794539 | 1 | 0 |  |  | [] | 0 | 2018-04-12 17:56:34.572345+00:00 | 2018-04-17 10:26:08.972675+00:00 | 2018-04-16 20:10:59.456666+00:00
210 | Fix issue where seller thumbnail displays on seller page but not on individual seller page |  | 204 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1523555898969 | 1 | 0 |  |  | [] | 0 | 2018-04-12 17:58:19.010805+00:00 | 2018-04-14 11:36:16.526891+00:00 | 2018-04-14 11:36:10.607263+00:00
211 | Remove the report test page link from login page when finished with it |  | 204 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1523556011902 | 2 | 0 |  |  | [] | 0 | 2018-04-12 18:00:11.971655+00:00 | 2018-04-16 12:34:55.501777+00:00 | 2018-04-16 12:34:55.507412+00:00
213 | Create up-to-date ERD to represent final data structure |  | 212 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | T-Dog | Thomas Makey | Closed | FALSE | TRUE | 1523556476623 | 0 | 0 |  |  | [] | 0 | 2018-04-12 18:07:56.667219+00:00 | 2018-04-17 11:28:39.764939+00:00 | 2018-04-17 11:28:39.772188+00:00
214 | Screenshot ERD and add to folder as "final ERD" or similar |  | 212 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | T-Dog | Thomas Makey | Closed | FALSE | TRUE | 1523556529383 | 1 | 0 |  |  | [] | 0 | 2018-04-12 18:08:49.475626+00:00 | 2018-04-17 11:28:42.825772+00:00 | 2018-04-17 11:28:42.831962+00:00
215 | Check for duplicate code from suspected de-syncing issue |  | 204 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1523556824923 | 3 | 0 |  |  | [] | 0 | 2018-04-12 18:13:44.975273+00:00 | 2018-04-14 12:50:43.835695+00:00 | 2018-04-14 12:50:43.849267+00:00
216 | Investigate use of Foundation's circular image class on product and seller page |  | 206 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1523556951804 | 2 | 0 |  |  | [] | 0 | 2018-04-12 18:15:51.840983+00:00 | 2018-04-14 12:51:14.185207+00:00 | 2018-04-14 12:51:14.191156+00:00
218 | Build test page on student server that pulls from APEX version of the database |  | 217 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1523557208643 | 0 | 0 |  |  | [] | 0 | 2018-04-12 18:20:08.686999+00:00 | 2018-04-14 13:46:32.144096+00:00 | 2018-04-14 13:46:32.152984+00:00
219 | Build relevant SQL queries in APEX, testing in SQL Commands, ready for final website version deployment |  | 217 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1523557246219 | 1 | 0 |  |  | [] | 0 | 2018-04-12 18:20:46.251737+00:00 | 2018-04-16 12:26:39.579335+00:00 | 2018-04-16 12:26:39.589298+00:00
221 | Remove code remaining in php files that was generated during the construction of the site and serves no further purpose (not inc. code built for testing purposes) |  | 220 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1523557614698 | 0 | 0 |  |  | [] | 0 | 2018-04-12 18:26:54.733327+00:00 | 2018-04-14 11:34:15.793492+00:00 | 2018-04-14 11:34:15.800905+00:00
222 | Ensure that all code is appropriately commented |  | 220 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | AndrewHeath | Andrew Heath | Closed | FALSE | TRUE | 1523557632958 | 1 | 0 |  |  | [] | 0 | 2018-04-12 18:27:12.999159+00:00 | 2018-04-14 11:34:17.379521+00:00 | 2018-04-14 11:34:17.389195+00:00
224 | Build portfolio page that meets the specification of the mark scheme |  | 223 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1523557857765 | 1 | 0 |  |  | [] | 0 | 2018-04-12 18:30:57.819862+00:00 | 2018-04-17 08:46:07.117126+00:00 | 2018-04-14 16:54:52.842007+00:00
225 | Style portfolio page in a professional, content relevant, fashion |  | 223 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1523557913481 | 2 | 0 |  |  | [] | 0 | 2018-04-12 18:31:53.521578+00:00 | 2018-04-14 17:02:44.722369+00:00 | 2018-04-14 17:02:39.577306+00:00
226 | Portfolio page is index.html and contains link to website |  | 223 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | humanmale | Dylan Ellis | Closed | FALSE | TRUE | 1523557983365 | 0 | 0 |  |  | [] | 0 | 2018-04-12 18:33:03.403459+00:00 | 2018-04-14 16:54:58.718267+00:00 | 2018-04-14 16:54:58.724250+00:00
228 | Research what personas are in the context of an e-commerce website to gain full understanding |  | 227 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1523558569967 | 0 | 0 |  |  | [] | 0 | 2018-04-12 18:42:50.006446+00:00 | 2018-04-17 17:27:35.053472+00:00 | 2018-04-17 15:13:33.210211+00:00
229 | Derive relevant personas |  | 227 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1523558586077 | 1 | 0 |  |  | [] | 0 | 2018-04-12 18:43:06.111067+00:00 | 2018-04-17 17:55:28.221605+00:00 | 2018-04-17 17:55:17.595730+00:00
230 | Explain how website appeals to the personas |  | 227 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | HabibKhan | Habib Khan | Closed | FALSE | TRUE | 1523558605578 | 2 | 0 |  |  | [] | 0 | 2018-04-12 18:43:25.615960+00:00 | 2018-04-17 17:55:26.379377+00:00 | 2018-04-17 17:55:15.051097+00:00
233 | Create tables of current customer and seller passwords, apply sha1 and salt |  | 232 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1523716041908 | 0 | 0 |  |  | [] | 0 | 2018-04-14 14:27:21.968729+00:00 | 2018-04-14 14:50:00.991906+00:00 | 2018-04-14 14:50:00.998111+00:00
234 | Apply sha1 hash (and salt) security to login system |  | 232 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1523716095221 | 1 | 0 |  |  | [] | 0 | 2018-04-14 14:28:15.257195+00:00 | 2018-04-14 15:08:03.518105+00:00 | 2018-04-14 15:08:02.067045+00:00
235 | Test with single login then alter db (mysql and APEX) to hold correct hashed passwords |  | 232 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1523716205959 | 2 | 0 |  |  | [] | 0 | 2018-04-14 14:30:06.013890+00:00 | 2018-04-14 16:24:18.522680+00:00 | 2018-04-14 16:24:18.529015+00:00
237 | Create application in apex to hold report of business stats |  | 236 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1523908106692 | 0 | 0 |  |  | [] | 0 | 2018-04-16 19:48:26.759480+00:00 | 2018-04-16 19:51:51.191362+00:00 | 2018-04-16 19:51:51.202156+00:00
238 | style report to match website |  | 236 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1523908124857 | 1 | 0 |  |  | [] | 0 | 2018-04-16 19:48:44.917365+00:00 | 2018-04-16 19:51:52.558384+00:00 | 2018-04-16 19:51:52.571918+00:00
239 | build content and sql |  | 236 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1523908136969 | 2 | 0 |  |  | [] | 0 | 2018-04-16 19:48:57.032095+00:00 | 2018-04-16 19:51:54.496760+00:00 | 2018-04-16 19:51:54.516343+00:00
240 | add links to and from admin panel on website |  | 236 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1523908149201 | 3 | 0 |  |  | [] | 0 | 2018-04-16 19:49:09.266167+00:00 | 2018-04-16 19:51:58.625289+00:00 | 2018-04-16 19:51:58.634163+00:00
241 | create security profile for application and use isset on adminhome to prevent access without login |  | 236 | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | Closed | FALSE | TRUE | 1523908188223 | 4 | 0 |  |  | [] | 0 | 2018-04-16 19:49:48.261293+00:00 | 2018-04-16 19:52:01.072814+00:00 | 2018-04-16 19:52:01.082143+00:00