## userstories (1)
ref | subject | description | sprint | sprint_estimated_start | sprint_estimated_finish | owner | owner_full_name | assigned_to | assigned_to_full_name | status | is_closed | back-points | design-points | front-points | ux-points | total-points | backlog_order | sprint_order | kanban_order | created_date | modified_date | finish_date | client_requirement | team_requirement | attachments | generated_from_issue | external_reference | tasks | tags | watchers | voters
4 | Logo | Design logo for Independent Onion, and basket icon | Week 1 | 2018-02-01 | 2018-02-14 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE |  | 10 |  |  | 10 | 1517509229664 | 3 | 1517509229655 | 2018-02-01 18:20:29.685139+00:00 | 2018-02-01 18:28:01.102921+00:00 | 2018-02-07 12:32:18.327867+00:00 | FALSE | TRUE | 0 |  |  | 11,12 |  | [] | 0
5 | Db Tables | Come up with prototype tables and columns (w/ relationships) in the meeting we said: user (with admin rights column), seller, customer, listings, order and anything else you might think we need | Week 1 | 2018-02-01 | 2018-02-14 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | 10 |  |  |  | 10 | 1517509331722 | 2 | 1517509331715 | 2018-02-01 18:22:11.746278+00:00 | 2018-02-01 18:35:26.637922+00:00 | 2018-02-07 12:32:24.702210+00:00 | FALSE | TRUE | 0 |  |  | 10,14 |  | [] | 1
6 | C9.io workspace | Create new php workspace and share with group. | Week 1 | 2018-02-01 | 2018-02-14 | NoSquirrels | Benjamin Eversfield | NoSquirrels | Benjamin Eversfield | In progress | TRUE | 10 |  |  |  | 10 | 1517509557981 | 1 | 1517509557972 | 2018-02-01 18:25:58.024591+00:00 | 2018-02-01 18:37:28.266610+00:00 | 2018-02-03 12:10:05.999919+00:00 | FALSE | TRUE | 0 |  |  | 8,13,15 |  | [] | 0
7 | Template | Create draft Moqup template of front page | Week 1 | 2018-02-01 | 2018-02-14 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE |  | 10 | 10 |  | 20 | 1517509757408 | 0 | 1517509757399 | 2018-02-01 18:29:17.437741+00:00 | 2018-02-01 18:29:23.047280+00:00 | 2018-02-04 19:40:56.519625+00:00 | FALSE | TRUE | 0 |  |  | 9 |  | [] | 0
16 | build first version of the db | Create a first pass at the database that contains all current tables and minimal test data | Sprint 2 | 2018-02-08 | 2018-02-22 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | 10 |  |  |  | 10 | 1518114612660 | 6 | 1518114612652 | 2018-02-08 18:30:12.687928+00:00 | 2018-02-08 18:51:51.559727+00:00 | 2018-02-24 12:39:49.967385+00:00 | FALSE | FALSE | 0 |  |  | 17,18,19,23 |  | [] | 0
20 | I am a colour scheme and i want to colour scheme | Create and test a colour scheme that is fitting with the product but offers a fresh, crisp and no clutter interface | Sprint 2 | 2018-02-08 | 2018-02-22 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE |  | 10 |  |  | 10 | 8 | 5 | 1518115473496 | 2018-02-08 18:44:33.531777+00:00 | 2018-02-08 18:51:56.436179+00:00 | 2018-02-20 23:28:35.815243+00:00 | FALSE | TRUE | 0 |  |  | 21,22,38 |  | [] | 0
24 | Project charter | Write project charter and upload to c9 | Sprint 2 | 2018-02-08 | 2018-02-22 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE |  | 10 |  |  | 10 | 1518116472669 | 0 | 1518116472661 | 2018-02-08 19:01:12.709972+00:00 | 2018-02-08 19:01:18.110407+00:00 | 2018-02-11 12:00:30.066566+00:00 | FALSE | FALSE | 0 |  |  | 25 |  | [] | 0
26 | Page audit | define pages for current vision of site and begin development on non-team dependant pages | Sprint 2 | 2018-02-08 | 2018-02-22 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | 10 |  |  |  | 10 | 1518116679245 | 3 | 1518116679237 | 2018-02-08 19:04:39.281003+00:00 | 2018-02-08 19:04:45.624954+00:00 | 2018-02-21 22:11:32.590870+00:00 | FALSE | TRUE | 0 |  |  | 27,28,39,41 |  | [] | 0
29 | creation of user stories | create user stories to populate backlog | Sprint 2 | 2018-02-08 | 2018-02-22 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE |  | 10 |  |  | 10 | 1518117314079 | 1 | 1518117314072 | 2018-02-08 19:15:14.098860+00:00 | 2018-02-08 19:15:20.223911+00:00 | 2018-02-14 11:16:04.788527+00:00 | FALSE | FALSE | 0 |  |  | 30 |  | [] | 0
31 | generate database entries | Create data for the database allowing functionality and design to be properly tested and implemented. | Sprint 2 | 2018-02-08 | 2018-02-22 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | 10 |  |  |  | 10 | 1518117442379 | 2 | 1518117442372 | 2018-02-08 19:17:22.403027+00:00 | 2018-02-08 19:17:26.712142+00:00 | 2018-02-16 14:16:58.377125+00:00 | FALSE | TRUE | 0 |  |  | 32,33 |  | [] | 0
34 | Develop site structure | Develop responsive front page | Sprint 2 | 2018-02-08 | 2018-02-22 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | 10 |  |  |  | 10 | 1518118028864 | 4 | 1518118028857 | 2018-02-08 19:27:08.901026+00:00 | 2018-02-08 19:27:13.985418+00:00 | 2018-02-24 12:39:40.172591+00:00 | FALSE | TRUE | 0 |  |  | 35,36,40 |  | [] | 0
88 | Finalise colour scheme |  | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | [5 empty] | 1519477021976 | 8 | 1519477021970 | 2018-02-24 12:57:01.998534+00:00 | 2018-02-24 12:58:27.279400+00:00 | 2018-03-01 13:04:49.544318+00:00 | FALSE | FALSE | 0 |  |  | 90 |  | [] | 0
91 | Develop Search Facility |  | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | [5 empty] | 1519477161095 | 7 | 1519477161089 | 2018-02-24 12:59:21.115035+00:00 | 2018-02-24 13:05:21.249552+00:00 | 2018-02-27 21:44:58.849482+00:00 | FALSE | FALSE | 0 |  |  | 89,92,93,94,95 |  | [] | 0
96 | Image upload facility |  | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | [5 empty] | 1519477627026 | 6 | 1519477627020 | 2018-02-24 13:07:07.052549+00:00 | 2018-02-24 13:11:36.365162+00:00 | 2018-03-01 13:11:53.445029+00:00 | FALSE | TRUE | 0 |  |  | 97,98 |  | [] | 0
99 | Create Seller Page |  | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | [5 empty] | 1519478091616 | 0 | 1519478091610 | 2018-02-24 13:14:51.640294+00:00 | 2018-02-24 13:18:29.596185+00:00 | 2018-02-27 17:10:12.573194+00:00 | FALSE | TRUE | 0 |  |  | 100101102 |  | [] | 0
103 | Database population |  | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | [5 empty] | 1519478367813 | 5 | 1519478367807 | 2018-02-24 13:19:27.852518+00:00 | 2018-02-24 13:23:33.522317+00:00 | 2018-03-01 13:11:49.546469+00:00 | FALSE | TRUE | 0 |  |  | 104105106125 |  | [] | 0
107 | Create Product listings page |  | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | [5 empty] | 1519478949813 | 1 | 1519478949807 | 2018-02-24 13:29:09.833132+00:00 | 2018-02-24 13:32:46.271150+00:00 | 2018-02-26 15:12:04.298346+00:00 | FALSE | TRUE | 0 |  |  | 108109110 |  | [] | 0
111 | Create Items page |  | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | [5 empty] | 1519479222494 | 3 | 1519479222489 | 2018-02-24 13:33:42.518938+00:00 | 2018-02-24 13:43:04.800789+00:00 | 2018-03-01 13:11:45.899343+00:00 | FALSE | TRUE | 0 |  |  | 112113114 |  | [] | 0
115 | Add trigger and data to db |  | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | [5 empty] | 1519479899932 | 2 | 1519479899926 | 2018-02-24 13:44:59.956020+00:00 | 2018-02-24 13:58:36.414505+00:00 | 2018-02-27 17:19:41.337613+00:00 | FALSE | TRUE | 0 |  |  | 116117118119120 |  | [] | 0
121 | Create shopping basket / order system |  | Sprint 3 aka Timothy | 2018-02-22 | 2018-02-28 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | [5 empty] | 1519480852263 | 4 | 1519480852257 | 2018-02-24 14:00:52.288001+00:00 | 2018-02-24 14:05:01.998669+00:00 | 2018-02-27 14:46:10.387193+00:00 | FALSE | TRUE | 0 |  |  | 122123124 |  | [] | 0
126 | Populate Products Table |  | Sprint 4 aka Ronald | 2018-03-01 | 2018-03-07 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | [5 empty] | 1519924479404 | 4 | 1519924479398 | 2018-03-01 17:14:39.434603+00:00 | 2018-03-01 17:15:12.379197+00:00 | 2018-03-06 12:10:23.545961+00:00 | FALSE | FALSE | 0 |  |  | 127 |  | [] | 0
128 | Acquire Onion Imagery |  | Sprint 4 aka Ronald | 2018-03-01 | 2018-03-07 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | [5 empty] | 1519924544197 | 5 | 1519924544191 | 2018-03-01 17:15:44.222497+00:00 | 2018-03-01 17:16:33.178533+00:00 | 2018-03-06 12:10:29.741182+00:00 | FALSE | TRUE | 0 |  |  | 129130 |  | [] | 0
131 | Reg form logistics |  | Sprint 4 aka Ronald | 2018-03-01 | 2018-03-07 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | [5 empty] | 1519924680660 | 3 | 1519924680655 | 2018-03-01 17:18:00.685066+00:00 | 2018-03-01 17:18:56.810467+00:00 | 2018-03-21 14:30:45.303134+00:00 | FALSE | TRUE | 0 |  |  | 132133 |  | [] | 0
134 | Code cleaning |  | Sprint 4 aka Ronald | 2018-03-01 | 2018-03-07 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | [5 empty] | 1519924774885 | 0 | 1519924774879 | 2018-03-01 17:19:34.914129+00:00 | 2018-03-01 17:22:56.974348+00:00 | 2018-03-05 13:29:04.118091+00:00 | FALSE | TRUE | 0 |  |  | 1.3514e+17 |  | [] | 0
141 | Listings, listings and listings |  | Sprint 4 aka Ronald | 2018-03-01 | 2018-03-07 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | [5 empty] | 1519925017717 | 2 | 1519925017712 | 2018-03-01 17:23:37.778950+00:00 | 2018-03-01 17:24:11.039009+00:00 | 2018-03-21 14:30:44.458655+00:00 | FALSE | TRUE | 0 |  |  | 142 |  | [] | 0
143 | Personal welcome screens |  | Sprint 4 aka Ronald | 2018-03-01 | 2018-03-07 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | [5 empty] | 1519925087111 | 1 | 1519925087105 | 2018-03-01 17:24:47.138808+00:00 | 2018-03-01 17:27:16.027352+00:00 | 2018-03-21 14:30:43.558495+00:00 | FALSE | TRUE | 0 |  |  | 144145 |  | [] | 0
146 | As a customer I want feedback that the purchase process was successful | Acceptance Criteria: 1. Customer can complete purchase and receive unique order number 2. If purchase fails, user will be informed and returned to the basket where the contents will remain 3. Customer should not be able to generate order number without items in the basket | Sprint 5 aka Melanie | 2018-03-21 | 2018-03-27 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | 20 |  | 10 | 20 | 50 | 1521643103753 | 5 | 1521643103750 | 2018-03-21 14:38:23.787144+00:00 | 2018-03-21 17:40:43.038978+00:00 | 2018-03-29 16:38:49.690446+00:00 | FALSE | TRUE | 0 |  |  | 147150 |  | [] | 0
151 | As a Habib I can find images for the seller table | Acceptance Criteria: 1. Each Seller has an individual, business relevant image to be displayed to the user 2. Images do not exceed size restriction 3. Images are sensibly compressed to have a small data footprint and acceptable visual qualilty | Sprint 5 aka Melanie | 2018-03-21 | 2018-03-27 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE |  | 10 | 20 |  | 30 | 3 | 0 | 1521652264117 | 2018-03-21 17:11:04.154633+00:00 | 2018-03-21 17:14:36.693327+00:00 | 2018-03-29 16:58:35.026204+00:00 | FALSE | TRUE | 0 |  |  | 152153154 |  | [] | 0
155 | As a seller I can view and amend my details | Acceptance Criteria: 1. Seller is correctly redirected to appropriate seller home on successful login. 2. Correct information is pulled from database. 3. Amend functionality shows seller currently stored information and can be successfully altered. | Sprint 5 aka Melanie | 2018-03-21 | 2018-03-27 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE |  | 20 | 20 | 10 | 50 | 1521652654241 | 3 | 1521652654238 | 2018-03-21 17:17:34.267832+00:00 | 2018-03-21 17:27:41.516265+00:00 | 2018-03-29 17:22:07.149532+00:00 | FALSE | TRUE | 0 |  |  | 156157158 |  | [] | 0
159 | As a customer I am presented with consistent and neat styling throughout my onion interlude | Acceptance Criteria: 1. User does not notice any design/ui anomalies on their journey through the site. 2. Styling rules defined on home page are consistent through out. 3. Pages load correctly | Sprint 5 aka Melanie | 2018-03-21 | 2018-03-27 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE |  | 40 |  | 10 | 50 | 1521653406264 | 1 | 1521653406261 | 2018-03-21 17:30:06.298032+00:00 | 2018-03-21 17:40:04.974714+00:00 | 2018-03-29 17:18:22.754667+00:00 | FALSE | TRUE | 0 |  |  | 160161162163 |  | [] | 0
164 | As an admin I can action basic admin functionality through the website | Acceptance Criteria: 1. Only admin account can access admin page 2. Admin has full access to data 3. Possible operations on data are clear 4. Data retrieved and changes to database are successful each time | Sprint 5 aka Melanie | 2018-03-21 | 2018-03-27 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | 20 |  | 20 | 10 | 50 | 1521654284668 | 2 | 1521654284665 | 2018-03-21 17:44:44.884566+00:00 | 2018-03-21 17:52:30.021001+00:00 | 2018-03-29 10:06:04.480362+00:00 | FALSE | TRUE | 0 |  |  | 165166167 |  | [] | 0
168 | As a customer I can see individual images for products/customers/sellers | Acceptance Criteria: 1. All sections of website requiring an image have one 2. Correct Images are displayed 3. Apex returns no errors on running of script | Sprint 6 aka Deborah | 2018-03-29 | 2018-04-04 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE |  |  | 10 |  | 10 | 1522345152513 | 5 | 1522345152511 | 2018-03-29 17:39:12.537790+00:00 | 2018-03-29 17:42:48.499248+00:00 | 2018-04-05 09:55:59.659253+00:00 | FALSE | TRUE | 0 |  |  | 169170171 |  | [] | 0
172 | #159 As a customer I am presented with consistent and neat styling throughout my onion interlude | Acceptance Criteria: 1. User does not notice any design/ui anomalies on their journey through the site. 2. Styling rules defined on home page are consistent through out. Pages load correctly. | Sprint 6 aka Deborah | 2018-03-29 | 2018-04-04 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE |  | 10 |  |  | 10 | 1522345426692 | 0 | 1522345426689 | 2018-03-29 17:43:46.718677+00:00 | 2018-03-29 18:16:45.700852+00:00 | 2018-04-05 11:39:56.501540+00:00 | FALSE | TRUE | 0 |  |  | 173174187 |  | [] | 0
175 | As a seller my best reviews are displayed on my seller home page in a visually appealing fashion | Acceptance Criteria 1. review boxes display evenly and correctly 2. text doesn't leave div 3. best reviews pulled from db | Sprint 6 aka Deborah | 2018-03-29 | 2018-04-04 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE |  | 5 |  |  | 5 | 1522347496477 | 4 | 1522347496474 | 2018-03-29 18:18:16.501139+00:00 | 2018-03-29 18:21:06.077686+00:00 | 2018-03-30 13:53:36.974261+00:00 | FALSE | TRUE | 0 |  |  | 176 |  | [] | 0
177 | Team Req: Build test page for oci connection test | Acceptance Criteria: 1. page code is consistent with requirements and ready for deployment | Sprint 6 aka Deborah | 2018-03-29 | 2018-04-04 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | 5 |  |  |  | 5 | 1522347654474 | 2 | 1522347654471 | 2018-03-29 18:20:54.498825+00:00 | 2018-03-30 12:08:20.827792+00:00 | 2018-04-04 14:32:14.395591+00:00 | FALSE | TRUE | 0 |  |  | 178179 |  | [] | 0
180 | As a seller I can view and amend my details | Acceptance Criteria: 1. Seller is correctly redirected to appropriate seller home on successful login. 2. Correct information is pulled from database. 3. Amend functionality shows seller currently stored information and can be successfully altered. | Sprint 6 aka Deborah | 2018-03-29 | 2018-04-04 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE |  | 5 |  | 5 | 10 | 1522347943445 | 3 | 1522347943443 | 2018-03-29 18:25:43.495847+00:00 | 2018-03-29 18:27:42.619186+00:00 | 2018-04-05 14:53:08.212301+00:00 | FALSE | TRUE | 0 |  |  | 181182183 |  | [] | 0
184 | As an admin I can update a seller or customer record from the admin panel | Acceptance Criteria: 1. update option sits neatly with delete option 2. page redirects to correctly populated page 3. update sql functions correctly, main admin page shows new information in table. | Sprint 6 aka Deborah | 2018-03-29 | 2018-04-04 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | 10 |  |  |  | 10 | 1522348171194 | 1 | 1522348171192 | 2018-03-29 18:29:31.232377+00:00 | 2018-03-29 18:35:36.792356+00:00 | 2018-04-02 11:25:58.360442+00:00 | FALSE | TRUE | 0 |  |  | 185186 |  | [] | 0
188 | Team Goal: Produce website personas documentation | Acceptance criteria: 1. The final document is well researched, accurate, well-written and, once presented to the team, is agreed upon as accurate and good. | Sprint 7 aka Wilhelm | 2018-04-05 | 2018-04-12 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | 10 |  |  |  | 10 | 1522950536604 | 6 | 1522950536601 | 2018-04-05 17:48:56.633118+00:00 | 2018-04-05 18:21:42.484494+00:00 | 2018-04-12 08:57:37.916555+00:00 | FALSE | TRUE | 0 |  |  | 189 |  | [] | 0
192 | Team Goal: Fix admin amendment form display issue | Acceptance criteria 1. the amendment form page loads within the homepage frame | Sprint 7 aka Wilhelm | 2018-04-05 | 2018-04-12 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE |  | 2 |  |  | 2 | 1522950798313 | 2 | 1522950798310 | 2018-04-05 17:53:18.345117+00:00 | 2018-04-05 18:21:45.910232+00:00 | 2018-04-08 11:31:56.898139+00:00 | FALSE | TRUE | 0 |  |  | 193 |  | [] | 0
194 | As a user I cannot access functionality not presently available to me | Acceptance Criteria: 1. user not logged in can't access the basket functionality (and therefore not affect quantity amounts etc) 2. user not logged in is redirected to login 3. Seller/admin can use customer functionality | Sprint 7 aka Wilhelm | 2018-04-05 | 2018-04-12 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE |  |  | 8 |  | 8 | 1522950798314 | 3 | 1522951050969 | 2018-04-05 17:57:30.999540+00:00 | 2018-04-05 18:23:26.443208+00:00 | 2018-04-08 13:14:35.999979+00:00 | FALSE | TRUE | 0 |  |  | 195 |  | [] | 0
196 | Team Goal: update ERD | Acceptance Criteria: 1. New ERD reflects current data system | Sprint 7 aka Wilhelm | 2018-04-05 | 2018-04-12 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | 10 |  |  |  | 10 | 1522951380428 | 0 | 1522951380425 | 2018-04-05 18:03:00.502670+00:00 | 2018-04-05 18:21:57.535071+00:00 | 2018-04-12 17:48:00.801127+00:00 | FALSE | TRUE | 0 |  |  | 197 |  | [] | 0
198 | As a user I feel welcomed to the site as part of a personalised experience. | Acceptance Criteria: 1. Nav bar displays name for logged in user, relevant to current user 2. Seller can access their personal home page from the nav bar. | Sprint 7 aka Wilhelm | 2018-04-05 | 2018-04-12 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE |  | 10 |  |  | 10 | 1522951553957 | 1 | 1522951553953 | 2018-04-05 18:05:53.991636+00:00 | 2018-04-05 18:21:54.684551+00:00 | 2018-04-11 07:32:27.328417+00:00 | FALSE | TRUE | 0 |  |  | 199200 |  | [] | 0
201 | Team Goal: Research Apex Reports page for site | Acceptance Criteria: 1. Report back to team on possibilities of Apex Reports on site. | Sprint 7 aka Wilhelm | 2018-04-05 | 2018-04-12 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE |  |  |  | 10 | 10 | 1522952093877 | 4 | 1522952093874 | 2018-04-05 18:14:53.906845+00:00 | 2018-04-05 18:22:00.752848+00:00 | 2018-04-11 14:55:18.830186+00:00 | FALSE | TRUE | 0 |  |  | 190191202203 |  | [] | 0
204 | As a user I am face with a bug-free design to incite confidence in the website | Acceptance Criteria: 1. When viewing the front page of the website the latest onions and top sellers images load and remain visible 2. Seller image loads consistently on individual seller page 3. Report test page link no longer displays on login page 4. Pages do not display the result of duplicated code anywhere on the website | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE |  |  | 3 |  | 3 | 2 | 3 | 1523555439135 | 2018-04-12 17:50:39.171239+00:00 | 2018-04-12 18:46:32.230668+00:00 | 2018-04-16 12:34:55.538137+00:00 | FALSE | TRUE | 0 |  |  | 205210211215 |  | [] | 0
206 | As a user I am presented with neat and consistent styling | Acceptance Criteria: 1. Headers on page sections sit within the central content column 2. Product page looks neat, organised and "full" 3. All buttons have the same styling 4. Decision reached on circular images, reported to team, team agrees with decision, decision implemented. | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE |  | 3 |  |  | 3 | 1523555706080 | 0 | 1523555706077 | 2018-04-12 17:55:06.114936+00:00 | 2018-04-12 18:46:36.351837+00:00 | 2018-04-17 08:44:56.789770+00:00 | FALSE | TRUE | 0 |  |  | 207208209216 |  | [] | 0
212 | TEAM GOAL: Produce up-to-date ERD | Acceptance Criteria: 1. ERD is 100% accurate to the data system 2. ERD is presented int he correct folder | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | 1 |  |  |  | 1 | 1523556383257 | 4 | 1523556383255 | 2018-04-12 18:06:23.292881+00:00 | 2018-04-12 18:46:29.734894+00:00 | 2018-04-17 11:28:42.875732+00:00 | FALSE | TRUE | 0 |  |  | 213214 |  | [] | 0
217 | TEAM GOAL: Translate MySQL statements to Oracle SQL | Acceptance Criteria: 1. Test page connects to APEX account 2. SQL in test page uses APEX database 3. Correct records returned and behaviour of site is normal | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | 5 |  |  |  | 5 | 1523557114907 | 5 | 1523557114905 | 2018-04-12 18:18:34.990455+00:00 | 2018-04-12 18:46:27.243404+00:00 | 2018-04-16 12:26:39.639829+00:00 | FALSE | TRUE | 0 |  |  | 218219 |  | [] | 0
220 | TEAM GOAL: clean the code | Acceptance Criteria: 1. No purpose-less code remains 2. All code is well commented | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | 2 |  |  |  | 2 | 1523557533601 | 6 | 1523557533599 | 2018-04-12 18:25:33.640908+00:00 | 2018-04-12 18:46:22.953153+00:00 | 2018-04-14 11:34:17.425238+00:00 | FALSE | TRUE | 0 |  |  | 221222 |  | [] | 0
223 | TEAM GOAL: Porfotlio Page | Acceptance Criteria: 1. Portfolio page meets the specification 2. The team agrees on the styling 3. The page links to the website | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE |  |  | 5 |  | 5 | 1 | 7 | 1523557761388 | 2018-04-12 18:29:21.431437+00:00 | 2018-04-12 18:46:18.535224+00:00 | 2018-04-14 17:02:39.638869+00:00 | FALSE | TRUE | 0 |  |  | 224225226 |  | [] | 0
227 | TEAM GOAL: Produce personas documentation | Acceptance Criteria: 1. Personas are relevant to team's design intentions 2. Personas are clearly explained and their relevance to the site design is clear | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE |  | 2 |  |  | 2 | 1523558493279 | 8 | 1523558493277 | 2018-04-12 18:41:33.323607+00:00 | 2018-04-12 18:46:09.208253+00:00 | 2018-04-17 17:55:17.630010+00:00 | FALSE | TRUE | 0 |  |  | 228229230 |  | [] | 0
232 | As a customer my login credentials are securely encrypted | Acceptance Criteria: 1. Passwords are saved in hashed form 2. login system performs correctly | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | 3 |  |  |  | 3 | 1523716013910 | 1 | 1523716013909 | 2018-04-14 14:26:53.940897+00:00 | 2018-04-14 14:32:24.257281+00:00 | 2018-04-14 16:24:18.561045+00:00 | FALSE | TRUE | 0 |  |  | 233234235 |  | [] | 0
236 | As an admin I can review a website summary via APEX | Acceptance Criteria: 1. Only admin can access link to report 2. Admin panel cannot be accessed from APEX without admin login 3. Data displayed on report is accurate | Sprint 8 aka The Final Push | 2018-04-12 | 2018-04-18 | NoSquirrels | Benjamin Eversfield |  |  | New | TRUE | 3 | 2 |  |  | 5 | 0 | 2 | 1523908042593 | 2018-04-16 19:47:22.649820+00:00 | 2018-04-16 19:51:27.488207+00:00 | 2018-04-16 19:52:01.144200+00:00 | FALSE | TRUE | 0 |  |  | 237238239240241 |  | [] | 0